Rochdale and Oldham Maternity Voices Partnership Work Plan 23-24

| SERVICE USER LEAD KEY FOCUS AREAS – Listening to local voices (Rochdale / Oldham) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| AREA FOR ACTION | EXPECTED OUTCOME -success criteria | Timeline | RESCOURCES AVAILABLE | KEY PARTNERS WORKING WITH MVP | RESOURCES TO SUPPORT | ACTIONS/HOW THIS WILL BE ACHIEVED |
| Breast/Chest Feeding Support | Improved support both in hospital (postnatal ward) and once discharged in community. Rochdale and Oldham offering to feel more aligned in terms of quality of support provided | Ongoing- Brought Forward from 21-22/ 22-23 | Commitment from Trust to go for UNICEF acc. Barriers are staff availability and training. Inconsistency between Oldham and Rochdale funding streams Volunteer Advocates (Peer support qualified non medical) | Wendy Blackwood NCA Infant Feeding Team Health Visiting Teams Home Start Host Family Hubs -Rochdale | Awareness raising campaign and feedback ask for National Breastfeeding week Funding for Peer Support | Peer Support group has been cited to be seen as preferred method of support for breast/chest feeding service users. Rochdale Family Hub launch looking to recruit peer support B/F consultants as part of the program to better support and increase B/F rates. B/F welcome scheme launched for Rochdale, GW Volunteer Advocate supporting promotion and sign up of venues. Rochdale online article. Working towards UNICEF Baby friendly accreditation by 2025 |
| Health Visiting Team | Build better relationship/awareness between HV and MVP. Understand barriers/set up/funding around why there are inconsistencies in quality of care service provided across Rochdale and Oldham | Ongoing- Brought Forward from 21-22/ 22-23 | HW Rochdale Local networking | Health Visiting Teams Rochdale and Oldham | HV representation on our quarterly meetings. Contact details for Rochdale info shared | To create a raising awareness Campaign with HV in Rochdale and Oldham – Summer 2023 Have had interest from HV wanting to attend MVP meetings and connect to see how we can work better together. HV Teams have been restructured speak with lead around mapping this to show service users who their HV Team are. |
| Better support for Hyperemesis Gravidarum | Improved support for people suffering with HG. Better information from Trust regarding medication and risks involved. Clear mapping/Pathway of treatment Peer Support group | Ongoing- Brought Forward from 21-22/ 22-23 | Engagement Midwives Key Stakeholders NCA ROH Lived experience Service users | Trust ROMVP Volunteer Advocates ROMVP Service Users |  | Task and Finish group set up with lived exp SU involvement to ensure changes to current pathway address real life experiences and concerns. End of June completion date expected to be extended but good progress being made. HG to be added to list of high risk/complex pregnancies pathway which will ensure continuity of care and access to additional support. HG to be added to GP refresher knowledge to support better education/understanding of the condition and the appropriate treatment |
| NCA/TRUST: key areas ROMVP involved |  |  |  |  |  |  |
| Workstream update meetings | Regular monthly meetings booked in to allow sharing of updates between Trust and ROMVP and for actions to be review and followed up in response to SU Feedback – Achieve accountability and drive change based on SU Voice | ONGOING | -Trust NCA -Monthly Governance -Patient Experience -Monthly Board -Divisonal Assurance Board (DAB) -Engagement Midwives | DOM or Deputy DOM | Service User Feedback – Link for web form to gather Care Opinion Access On the ground Engagement sessions across Rochdale and Oldham Quarterly Meetings Social Media Campaigns #Feedback Friday | PPEG Monthly Meetings minuted with Actions in Action Log progress monitored to ensure feedback is acted upon. Key Themes/Comments fed back to Divisional Assurance Board monthly as part of Service User Voice report which combines Engagement MW and ROMVP SU Feedback for action Key Trends from feedback are identified and used to focus the theme of the quarterly meetings ensuring what matters most to service users is the main focus. |
| 15 Steps FOLLOW UP VISIT | MVP/Service User review of maternity departments across Rochdale Infirmary and ROH – resulting in report of findings, presentation to Trust and agreed actions to follow up | Deadline for Trust to provide update on action plan 30 June 2023 | ROMVP Engagement Midwives Patient Experience Deputy HOM | Heathwatch Rochdale Commissioners Dad Matters Service Users Ward Managers HOM | Report and recommendations | 15 steps taken place in both Oldham and Rochdale previous FY. Report and recs Follow up visit “Walk The Patch” Planned for Autumn 23 |
| Maternity Transformation Program Maternity Strat CQC Ockenden 2 | Ensure Service User Voice is represented and heard when making decisions on how future care/service offer should look Define how best practice maternity care should look going forward as business as usual Actions following CQC Report Compliance with all outstanding actions | Phase 2 roll out 2023 | Q: How will Trust ensure support for next FY, as ask is more | ROH LMS NCA |  |  |
| CNST | Provide supporting evidence of requirements met for CNST – desired outcome for Trust to be compliant | UPDATE DUE August 23 |  | Deputy Director Of Midwifery Northern Care Alliance |  | Childcare remuneration not in the ROMVP budget/ funding Trust to cover on ad hoc basis |
| ROMVP – LOCAL DEVELOPMENT |  |  |  |  |  |  |
| Quarterly ROMVP Meeting | Multi disciplinary meeting online to update service users on ROMVP workstreams, Progress, updates and provide opportunity to discuss directly with the Trust Rep any issues | March 23 July 23 September 23 January 24 March 24 Last Monday of Month – 8pm – 9:15pm |  | Healthwatch Rochdale Healthwatch Oldham ROMVP Chair and Vice Chair Service Users ROMVP Vol Advocates Professionals Organisations PIMH services | Social Media Website Networks | . Minutes and Action Logs. Agenda and minutes circulated and on web site. |
| Raise profile of ROMVP | Through on the ground engagement, events, social media, local community groups, Trust promotion (displays throughout hospital/clinics and on social media/website) | Ongoing |  | Healthwatch Rochdale & Oldham Action Together Local Community Groups NCA Trust Networks Commissioners Service Users ROMVP Volunteer Advocates | Existing groups in place Community Centres Stay and Play Wall Board in Rochdale Antenatal – update when required | Pop-up Banner provided Engagement f2f and via online Active awareness raising across Rochdale and Oldham via Networks |
| Recruit diverse group of ROMVP Volunteer Advocates | Attract a diverse range of people as engaged Volunteer Advocates which represent our local diverse communities Set up a #ROMVP100 | Ongoing Drive #4 July 2023 Summer 2023 | Current ROMVPs HWR Volunteer resource pack/induction | Healthwatch Rochdale Share with wider networks including Action Together, BAME forum, Faith and community partnership, LGTBQ Network | New Community Engagement Midwives in place to work alongside | New Volunteer Engagement Facilitator role to be filled by Oct 23 part of this role will be to actively recruit new advocates and manage current ones |
| Monthly Commissioner/Healthwatch contract update meetings | Track progress and highlight areas of importance/chance to escalate any barriers faced with work plan | Ongoing Monthly via Teams @1 hour |  | Healthwatch Rochdale ROMVP Chair, Vice Commissioners -Oldham -Rochdale | Monthly Highlight report |  |
| Engage with local community/gain feedback through listening events, surveys, ROMVP Topical Q&A sessions. Specific focus to be put on hearing voices of seldom heard. | To collect lived experience stories and feedback from women, birthing people and their families to feed into Maternity Strategy and wider maternity services. Creating opportunities for dialogue with people whom wouldn’t feedback via normal channels. | Ongoing | Healthwatch Oldham – Engagement Healthwatch Rochdale – Engagement ROMVP Vol Advocates – groups/orgs Local Networks | Healthwatch Rochdale/ Oldham ROMVP Vol Advocates Patient Experience Team NCA Local Community/ Faith Groups | Require More funding for interpreters/ room hire/ incentives for participation | Plan to host 4 listening events per annum via HW Oldham with HW Rochdale to mirror based on feedback Plans to regularly engage via informal drop ins at local group. Volunteer Engagement Facilitator role will map out 6 month engagement plan |
| Link in with NMV as and when required | Touch base and keep an eye on current issues nationally and take learnings from other MVPs | Ongoing | Laptop provided by HWRochdale | National Maternity Voices |  |  |
| ROMVP- LMS NETWORK INVOLVEMENT AND DEVELOPMENT |  |  |  |  |  |  |
| Ockenden 2 |  | Ongoing |  | Trust GMEC/LMS | Awaiting instructions/requirements regarding Ockenden 2 |  |
| Equity and Equality Workstream |  | Ongoing |  | Trust GMEC/LMS HWRochdale |  |  |
| Monthly GMEC MVP Update | Support and advice peer to peer opportunity to learn from other MVP Chairs locally | Ongoing | Laptop provided by HWRochdale |  | NMVP Facebook Chair Whatsapp GM & Eastern Cheshire Chair contact | Active in media groups. |
| Monthly NW MVP Update | Support and advice peer to peer opportunity to learn from other MVP Chairs Regionally | Ongoing | Laptop provided by HWRochdale |  | NMVP Facebook Chair Whatsapp Northwest Regional Chair contact | Active in media groups. |

Rochdale and Oldham Maternity Voices Partnership Quarterly meeting: Agendas and Minutes.

| Meeting and Date | Agenda | Minutes | Action Log Working docs |
| --- | --- | --- | --- |
| Meeting #9 Badgernotes 17.04.23 |  |  |  |
| Meeting #10 Meet the Advocates 26.06.23 |  |  |  |
| Meeting #11 Informed Choice 25.09.23 |  |  |  |
| Meeting #12 Infant feeding 18.12.23 |  |  |  |
| Meeting #13 March 2024 |  |  |  |